## Sheet1
THE LONDON BOROUGH OF BARNET (Granville Road) COMPULSORY PURCHASE ORDER 2018.
Objector 2 - Schedule of Communciation since Order made.
Date | Action | Outcome
30.1.18 | Email from Objector | Objector stated The Council has not responded to any letters, the Council has not send a legally binding document. Objector advised they are informed the Council will be responsible for costs for suryeyor, drafting letters, negotiation, representing at CPO plus disturbance, legal costs and statutory paments.
4.2.18 | Email from The Council | Sent copies of letters previously sent 27.9.17,16.10.17, 26.10.17, 4.1.18. Advised legally bindign agreeements had been issued and will request a further one and that HBPL will respond further.
12.2.18 | Letter from HBPL | responded to queries and re issued Contract.
13.2.18 | Letter from Objector to HBPL | Advised they have identified Solicitors, confirmed fees and await The Council approval to pay.
6.3.18 | Letter dated 5.3.18 sent via email from The Council | Full response to the objections. Email offered the opportunity to meet in person to discuss, offered 3 dates and offer of reasonable legal costs for a lawyer to attend meeting.
6.3.18 | Letter from Objectors to HBPL | Asking for response from letter dated 25.2.18
15.3.18 | Letter from HBPL | Agreeing to legal costs in connection to lease of the replacement storeroom.
19.3.18 | Email from The Council | Requesting if Objector had chance to review letter 5.3.18 and attend meeting.
19.3.18 | Email from Objector | requesting that their costs are paid for a meeting, and feel a meeting is 'pointless'. Confirmed they disagree with the valuation of the storeroom.
20.3.18 | Email from HBPL | Emailed copy of letter dated 19.3.18.
21.3.18 | Email from The Council | Advised The Council can meet at their home and can meet outside of office hours. Sent link to CPO guidance.
21.3.18 | Contract sent | Amended Contract and accompanying letter from HBPL sent to the Objectors
27.3.18 | Letter to HBPL | Letter from the Objectors' appointed solicitors confirming that they are acting in this matter
3.4.18 | Contract Sent | HBPL issued latest documents to solcitors
18.4.18 | Letter from Solicitors | Confirmng receipt
02.05.18 | Email from HBPL | HBPL chased Solicitors for a response.
09.05.18 | Letter from Solicitors | Confirming they have had no instructon from Objectors and are due to meet them on 20.5.18
05.06.18 | Letter from HBPL | Requesting feedback from Solicitors
05.06.18 | Telephone call with Solicitors | Confirmed meeting with the Objectors did not take place as Objectors are out of the Country and do not have instruction.